## Roadmap
Roadmap Nexyan | [9 empty] | Timeline
N° | Project | Milestones and actions | ISO Controls | Status | Priority | Owner | Effort |  | Remarks | 2024 | [8 empty] | 2025
| Project | [5 empty] | Infosentry | Nexyan |  | April | May | June | July | August | September | October | November | December | Januari | Februari | Maart | April | Mei | Juni | Juli
01 | Information security management system |  |  | Ongoing | Critical |  | 10.75 | 8
|  | MILESTONE: Context |  | Done
|  | Perform and document a context analysis (DESTEP / SWOT). | 4.1 Understanding the organization and its context | Done |  |  | 3 | 3
|  | Perform a stakeholder analysis | 4.2 Understanding the needs and expectations of interested parties | Done
|  | Define and document the scope of the management system and the Statement of Appplicability (SoA) | 4.1 Understanding the organization and its context | Done
4.3 Determining the scope of the ISMS
|  | Optional: Document the ISMS manual with underlying processes. | 4.1 Understanding the organization and its context | Done
|  | MILESTONE: Leadership |  | Done
|  | Document an information security policy which includes mission, vision, strategy, objectives, high-level responsibilities, management’s commitment, principles… Share & communicate the policy with all relevant stakeholders. Start with the Information security policy of Nexyan. | 5.1 Leadership and commitment | Done |  |  | 2 | 1.5
|  | Roles & responsibilities: Based on a RACI matrix, define and document the different roles with roles descriptions (with focus on responsibilities and authorities), organigram and a role matrix. Make someone responsible | 5.3 Organizational roles, responsibilities and authorities | Done
|  | MILESTONE: Planning |  | Done
|  | Risk analysis: Define a risk assessment framework (BIA-RCA) and do a risk analysis for information security. | 6.1 Actions to address risks and opportunities | Done |  |  | 3 | 2
|  | Risk treatment plan: Document and implement a risk treatment plan to mitigate, transfer, accept… the severe information security risks. | 6.1.3 Information Security Risk Treatment 8.3 Information security risk treatment | Done
|  | Define KPI's for information security: Define information security objectives which can be measured via KPI’s. The objectives can be shared via the policy and KPI’s should be monitored via the management review meetings. Integrate the plans to achieve the objectives in the underlying processes, policies, procedures… | 6.2 Information security objectives and planning to achieve them | Done
|  | MILESTONE: Support |  | Ongoing
|  | Resources: Dedicate and document the specific and formal resources for the establishment, implementation, maintenance and continual improvement of the Information security management system. | 7.1 Resources | Done |  |  | 1.5 | 0.5
|  | Competences: Document necessary competences and monitor needs. | 7.2 Competences | Done
|  | Awareness: Update the awareness and training plan. | 7.3 Awareness | Ongoing
|  | Define communication policy: Document a communication plan linked to the stakeholder analysis. | 7.4 Communication | Done
|  | Document management: Define, document and implement document management system : versioning, track of changes, approval flow, standardised templates, ownership… | 7.5 Documented Information | Done
|  | MILESTONE: Operations |  | Ongoing
|  | Ensure recurring tasks for the ISMS are planned and traceability of actions are documented. | 8.1 Operational planning and control | Ongoing |  |  | 0.25 | 0
|  | MILSTONE. Performance evaluation |  | Planned
|  | Monitoring activities (ISMS): Define monitoring activities to evaluate the ISMS. | 9.1 Monitoring, measurement, analysis and evaluation | Planned |  |  | 0.5 | 0.5
|  | Monitoring & report: Ensure monitoring is performed and reported during management review meetings. | 9.3 Management review | Planned
|  | Periodic management meeting: Organize periodically management meetings to monitor information security. | A.5.4 Management responsibilities | Done
|  | Organize internal audit: Document and implement an audit planning (scoping of yearly internal audits). | 9.2 Internal audit | Planned
|  | Address non-conformities: Remediating internal audit non-conformities. | 10.1 Nonconformity and corrective actions | Planned
|  | External audit: Yearly external audits. |  | Planned
|  | MILSTONE: Continious Improvements |  | Done
|  | Register non-conformities: Document and implement a register of non-conformities, complaints, deviations and corrective actions to strive for continuous improvement. | 10.2 Nonconformity and corrective actions | Done |  |  | 0.5 | 0.5
02 | Policy & organization |  |  | Ongoing | Medium |  | 1.5 | 1.5
|  | MILESTONE: Policy & Organisation |  | Done
|  | Appoint a security officer. | 5.3 Organizational roles, responsibilities and authorities | Done |  |  | 0.5 | 0.5
|  | Segregation of duties: Formalize segregation of duties and role descriptions. Include security responsibilities in function descriptions. | 5.3 Segregation of duties | Done
|  | Increase / strengthen contact with special interest groups: Ensure that there is sufficient internal knowledge to implement information security efficiently and effectively. Maintaining contact with special interest groups (e.g. newsletters from enisa, isaca, iapp... ) is a first step. Document and inventory all special interest groups. | 5.5 Contact with authorities | Done
|  | MILESTONE: Mobile Devices and teleworking |  | Ongoing
|  | Smartphones: Define policy for smartphone-use for work related activities. | 8.1 User endpoint devices | Done |  |  | 1 | 1
|  | BYOD: Update policy for BYOD | 8.1 User endpoint devices | Done
|  | Laptops: update policy for laptops: configuration settings, choices… If the laptop is configured by the employee itself, make sure it is monitored (4 eye principle). | 8.1 User endpoint devices | Ongoing
|  | Teleworking: Update policy for teleworking (use of 4G hotspot in case of insecure wifi). | 8.1 User endpoint devices | Done
03 | Information security incident management |  |  | Done | High |  | 1 | 1.5
|  | MILESTONE: Incident management procedures |  | Done
|  | Incident management procedure: Update the information security incident management procedure | 5.24 Information security incident management planning and preparation | Done |  |  | 1 | 1.5
|  | Include a data breach procedure (see project 7 in Privacy chapter) |  | Done
|  | Awareness program with focus on incidents & service delivery: Document the information security (and privacy) incident management procedure with clear responsibilities, incorporating incident reporting, registration and handling. Focus on notification forms, an incident classification and assessment framework, automated escalation and communication to end-users of lessons-learned. | 7.3 Awareness | Done
|  | Review and document the different roles of Nexyan for customer related incidents (second line helpdesk) and internal incidents (first line and owner). | 5.3 Organizational roles, responsibilities and authorities | Done
|  | Collection of evidence: Introduce collection of evidence and learning from incidents. | 5.28 Collection of evidence | Done
|  | Problem management process: Introduce a problem management process | 5.24 Information security incident management planning and preparation | Done
04 | Business Continuity Management |  |  | Ongoing | Medium |  | 2 | 1.5
|  | MILESTONE: Business impact analysis |  | Done
|  | Identify and document all time-critical operations and supporting people, facilities, IT, third parties and their dependencies (risk analysis). | 6.1 Actions to address risks and opportunities | Done |  |  | 1 | 0.5
|  | RTO & RPO: Evaluate the continuity risks and define RTO’s and RPO’s for all time-critical operations. | A.8.13 Information backup | Ongoing
|  | MILESTONE: Business continuity plan |  | Ongoing
|  | Business continuity plan: Document a business contuity plan for the critical processes. | 5.29 Information security during disruption | Done |  |  | 1 | 1
|  | Contracts critical suppliers: Make sure contracts of critical suppliers include sufficient requirements concerning availability, redundancy and business continuity testing. Contracts must involve financial penalties if metrics are missed. | 5.19 Information security in supplier relationships | Ongoing
|  | Business continuity test program: Set-up a business continuity test program (at least an annual test). | 5.29 Information security during disruption | Done
|  | Crisismanagement process: Document a crisis management process | 5.29 Information security during disruption | Done
05 | Operations Security |  |  | Open | Medium |  | 2.75 | 2.25
|  | MILESTONE: Operations security policy and processes |  | Open
|  | Operations security policy: Document policy 'operations security' including all controls. | 8.19 Installation of software on operational systems | Open |  |  | 0.5 | 0.25
|  | MILESTONE: Change management |  | Open
|  | Change management process: Document and implement a change management process, both for external changes (managed services) and internal changes (employees etc). | 8.32 Change management | Open |  |  | 0.5 | 0.25
|  | MILESTONE: Malware |  | Done
|  | Update and implement a company-wide malware protection policy. | 8.1 User endpoint devices | Done |  |  | 0 | 0.25
|  | MILESTONE: Backup |  | Done
|  | Formalize and test back-up and restore procedures. Document backup plan for internal software. Evaluate if this is sufficient for RTO/RPO. | 8.13 Information backup | Done |  |  | 0.5 | 0.5
|  | MILESTONE: Logging and monitoring |  | Done
|  | Logging & monitoring controls: Set-up logging and monitoring controls (especially for administrator / operator logs), incl. protection of logfiles. | 8.15 Logging | Done |  |  | 0.5 | 0.25
|  | Overview: Make an overview of all generated security logs. Evaluate if this is sufficient, focus on most critical applications and administrator accounts. | 8.15 Logging | Done
8.16 Monitoring activities
|  | Periodic review: Periodically audit the logs of critical applications to detect suspicious events. | 9.1 Monitoring, measurement, analysis and evaluation | Planned
|  | MILESTONE: Control of operational software |  | Done
|  | Restrictions software installation: Define restrictions on software installations on end-points | 8.1 User endpoint devices | Done |  |  | 0.5 | 0.5
|  | MILESTONE: Technical vulnerability management |  | Done
|  | Software updates: Make employees aware to update software when available. Monitor when deemed necessary. | 8.8 Management of technical vulnerabilities | Done |  |  | 0.25 | 0.25
|  | Patch management procedures: Formalize and implement patch management procedures. Make sure updates of OS on laptops are pushed. | 8.8 Management of technical vulnerabilities | Ongoing
06 | Asset Management, Equipment and User endpoint devices |  |  | Ongoing | High |  | 2.25 | 2.5
|  | MILESTONE: Responsibility for assets |  | Done
|  | Asset management policy: Document policy 'asset management' including all controls. | 5.10 Acceptable use of information and other associated assets | Done |  |  | 1 | 1
|  | Inventory: Inventory all assets (incl. test laptops, software, …) and assign ownership. | 5.9 Inventory of information and other associated assets | Done
|  | Flow asset: Make sure the history of each asset is clear. | 5.11 Return of assets | Done
|  | Acceptable use: Document acceptable use policies | 5.10 Acceptable use of information and other associated assets | Done
|  | MILESTONE: Information classification |  | Ongoing
|  | Information classification policy: Define the classification levels (confidentiality, integrity and availability) into an information classification policy. | 5.12 Classification of information | Done |  |  | 1 | 1
|  | Classify information based on classification level: Classify information owned by Nexyan in different classification levels of confidentiality, integrity and availability. | 5.9 Inventory of information and other associated assets | Planned
|  | Security measures for the different classification levels: Define and implement security measures for the different classification levels. The level of protection should take into account the lifecycle of information including phases such as creation, storage, distribution, deletion, archiving… | 5.12 Classification of information | Done
|  | MILESTONE: Media handling |  | Done
|  | Removable media: Document the use of removable media (USB-sticks and external hard disks). | 7.7 Clear desk and clear screen | Done |  |  | 0 | 0.25
|  | MDM: Consider mobile device management solutions / tools. | 8.1 User endpoint devices | Done
|  | MILESTONE: Equipment |  | Ongoing
|  | Disposal/reuse of laptops: Define and implement a secure process for the disposal/reuse of Macbooks, Windows and Linux devices | 7.8 Equipment siting and protection | Open |  |  | 0.25 | 0.25
|  | Laptop lock / Clear desk & clear screen: Create an awareness program about locking laptops when leaving and clean desks when leaving. Make sure laptops are automatically locked after 2 minutes. | 7.7 Clear desk and clear screen | Done
07 | Compliance and data governance |  |  | Ongoing | High |  | 1 | 0.75
|  | MILESTONE: Compliance process |  | Done
|  | Law- and legislation register: Document a law and legislation register to identify all applicable laws and legislations. | 5.31 Identification of legal, statutory, regulatory and contractual requirements | Done |  |  | 0.5 | 0.25
|  | MILESTONE: Roll out privacy compliance program |  | Planned
|  | Roll out privacy compliance program | 5.32 Intellectual property rights | Planned |  |  | 0 | 0.25
|  | MILESTONE: Information security reviews |  | Done
|  | Document and implement an audit planning (scoping of yearly internal audits). Perform yearly internal audits. | 5.35 Independant review of information security | Done |  |  | 0.5 | 0.25
|  | ​Prepare a penetration testing program with (at least) yearly web app penetration testing. Also bug bounty can be considered, but this brings the best results after an initial manual penetration test. | 5.36 Compliance with policies and standards for information security. | Open
08 | Human resources security |  |  | Done | Low |  | 1.5 | 2
|  | MILESTONE: HR processes |  | Done
|  | Procedure People In, People Out & People Change: Formalize hire to retire procedure from application until retirement. Ensure information security checks during People In (onboarding), People Out (offboarding) and People Change (change of role). | 6.2 Terms and conditions of employment | Done |  |  | 1.5 | 2
|  | Screening control: Integrate information security checks in the recruitment procedure. Include screening of system administrators or key personnel. | 6.1 Screening | Done
Review the work agreement and work regulations on responsibilities regarding data protection
|  | Disciplinary process: Formalize a disciplinary policy within Nexyan to take action in case of a data breach. | 6.4 Disciplinary process | Done
09 | Physical and environmental security + secure areas |  |  | Done | Medium |  | 1 | 1.5
|  | MILESTONE: Secure areas |  | Done
|  | Document physical security perimeters. Document security controls per zone in a physical and environmental security policy. | 7.1 Physical security perimeter | Done |  |  | 1 | 1.5
|  | Formalize processes regarding physical access rights and alarm codes. | 7.2 Physical entry controls | Done
10 | Access Management and Software & utility programs |  |  | Ongoing | High |  | 1.75 | 1.75
|  | MILESTONE: Policy for access management |  | Done
|  | Policy logical access control: Formalize a policy / process for access control (authorization, authentication, privileged access, rights management, review of access rights, (de)activation of accounts) | 5.15 Access control | Done |  |  | 1 | 0.5
|  | Accounts customer environment: Formalize and document management of accounts on customer environments | 5.15 Access control | Done
|  | MILESTONE: Accountmanagement |  | Planned
|  | Evaluation: Perform a periodic evaluation of the allocated rights and sleeping accounts (e.g. every quarter) and register the results. | 9.1 Monitoring, measurement, analysis and evaluation | Planned |  |  | 0 | 0.25
|  | MILESTONE: Rights management |  | Ongoing
|  | Document a CRUD matrix, based on roles and with all applications. After documentation, do a review to see if the need-to-know principle has been implemented. | 5.15 Access control | Ongoing |  |  | 0.25 | 0.5
|  | MILESTONE: Password management |  | Done
|  | Password policy: Formalize and implement a password policy | 5.15 Access control | Done |  |  | 0.5 | 0.5
|  | MFA: Implement MFA for privileged users, critical systems / information, utility programs or source codes | 5.15 Access control | Done
11 | Network Security |  |  | Ongoing | Medium |  | 0.75 | 0.75
|  | MILESTONE: Secure communications |  | Ongoing
|  | Communications security policy: Document policy 'communications security' including all controls. | 7.4 Communication | Open |  |  | 0.5 | 0.5
|  | Controls for information transfers: Set up controls for information transfers. Consider encryption solutions for e-mail or othe secure channels to share information with external parties. | 5.14 Information transfer | Done
|  | MILESTONE: Information management |  | Done
|  | Information management: develop guidelines around information management | 7.3 Awareness | Done |  |  | 0.25 | 0.25
|  | Storage & exchange of information: Guidelines for storage & exchange of information | 7.10 Storage media A.8.10 Information deletion | Done
12 | Supplier/procurement management and cloud security |  |  | Done | High |  | 3 | 1
|  | MILESTONE: supplier management |  | Done
|  | Document process: Define and document the whole supplier/procurement process. | 5.19 Information security in supplier relationships | Done |  |  | 3 | 1
|  | Security requirements in contracts: Include security requirements in supplier contracts (incl. SLA's, for example with Trustteam) | 5.19 Information security in supplier relationships | Done
|  | Formal evaluation: Implement a formal evaluation when selecting a new asset/supplier. | 5.22 Monitoring; review and change management of supplier services | Done
|  | Review: Formally review (at least yearly) and monitor supplier service quality, SLA's, security posture, … | 5.22 Monitoring; review and change management of supplier services | Planned
13 | Cryptography |  |  | Done | Low |  | 0.25 | 0.25
|  | MILESTONE: Cryptography policy |  | done
|  | Policy + Key management: Document policy 'cryptography' including all controls including the organization of encryption key management. | 8.24 Use of cryptography | Done |  |  | 0.25 | 0.25
14 | System acquisition, development and maintenance |  |  | Done | Critical |  | 2.5 | 1
|  | MILESTONE: System acquisition |  | done
|  | Formalize a secure acquisition procedure | 8.25 Secure development life cycle | Done |  |  | 1 | 0.25
|  | Information security analysis: Ensure that an information security analysis is conducted when acquiring new information systems or making changes to information systems | 8.26 Application security requirements | Done
|  | MILESTONE: Secure development |  | Open
|  | Define requirements a system has to comply with | 8.26 Application security requirements | Open |  |  | 1 | 0.25
|  | Methodology: Formalize development procedures (create a secure development methodology) | 8.25 Secure development life cycle | Open
|  | MILESTONE: Secure maintenance |  | Open
|  | Testing: Ensure that developments are adequately tested in a (separate) secure development environment. Define how acceptance testing should be performed in practice using formally defined acceptance criteria | 8.33 Test information | Open |  |  | 0.5 | 0.5
|  | Pentest Program: Pentest program rollout (annual) | 8.8 Management of technical vulnerabilities | Done
15 | Project management |  |  | Open | Medium |  | 2 | 1.5
|  | MILESTONE: Project process |  | Open
|  | Project management process: Formalize the project management process (operational) and document operating procedures from sales until closure of a project (incl. project change management, acceptance, aftercare process, registration of error ...) | 5.8 Information security in project management | Open |  |  | 1 | 1
|  | MILESTONE: Information security baseline |  | Open
|  | Statement of Work: Document the information security baseline on project level and integrate this in the State of Work. | 5.8 Information security in project management | Open |  |  | 1 | 0.5
|  | Integrate information security risks in the risk analysis on project level. | 5.8 Information security in project management | Open
Privacy
1 | Project Privacy Policy and Governance |  | Open |  | High |  | 4 | 5
|  | Create and implement a privacy policy that states how employees should handle personal information. | Open
|  | Create a document in which the roles and responsibilities are taken up, and check whether new roles need to be taken up within the organization (e.g. DPO). | Open
|  | Implement a section regarding data protection in the different policies regarding information security. | Open
|  | Establish a risk management process to systematically identify data protection and privacy risks and risk treatment plans. | Open
|  | Complete the register of processing activities with the processing activities carried out by Nexyan both as a controller (e.g., recruitment, HR management, website, etc.) and processor (e.g., projects for customers where personal data processing is in scope of the assignment). Add a “data location”-column in the template. | Open
|  | Establish a process and plan systematic reviews to keep the register up to date (e.g., in the event of new processing operations, adjustments to already existing processing operations, the use of new systems, …). | Open
2 | Project Awareness |  | Open |  | High |  | 1 | 2
|  | Draw up a code of conduct or guidelines for employees that indicates how personal data and sensitive data should be handled. | Open
|  | Conduct regular awareness initiatives for employees. To ensure demonstrability, it’s recommended to document these activities and track participation in awareness campaigns. Incorporate these into e-learning modules to be included in the onboarding process for new employees. | Open
3 | Project Data Governance |  | Open |  | Medium |  | 1 | 2
|  | Analyze the possibility and opportunity of pseudonymization when processing data in production development to strengthen the security and reduce the effects of a potential data breach. | Open
|  | Evaluate a reasonable period for the retention of personal data. Consider anonymization of data during long-term storage or archiving so that identification is no longer possible (and thus GDPR is not applicable anymore) or delete the data. | Open
4 | Project Interaction and rights management |  | Open |  | Medium |  | 2 | 3
|  | Develop a process so that it is clear how Amista can meet interaction requests from data subjects (both as a processor and controller e.g., employer). Implement e.g., a process that makes it possible to comply with requests from data subjects regarding the exercise of their rights within 30 days: | Open
o Right to information (Art. 13 and 14 GDPR)
o Right of access (Art. 15 GDPR)
o Right to rectification (Art. 16 GDPR)
o Right to erasure (Art. 17 GDPR)
o Right to restriction of processing (Art. 18 GDPR)
o Right to portability (Art. 20 GDPR)
o Right to object (Art. 21 GDPR)
o Right not to be subject to automated individual decision-making (Art. 22 GDPR)
|  | Analyze in which cases the abovementioned rights cannot be executed (e.g., personal data that is needed to execute a contract, personal data that is processed to comply with a legal obligation, …). Ensure that these cases are incorporated in the abovementioned process and clearly communicated towards data subjects. | Open
|  | Analyze per processing activity whether deletion of personal data (upon request of a data subject) is possible, how this can be technically executed, which 3rd parties are involved, …. | Open
5 | Project Third-Party Management |  | Open |  | Medium |  | 4 | 5
|  | Make an overview of parties with whom personal data is exchanged. Both parties that receive personal data from Nexyan, and organizations that provide data to Nexyan when applicable. | Open
|  | Provide a protection mechanism for data transfers outside the EEA when this becomes relevant. This can be evaluated by means of Data Transfer Impact Assessments where the risks of unlawful processing of personal data outside of the EEA can be assessed. Document these DTIAs and consider a (temporary) cessation of the processing activity if a third party does not offer sufficient guarantees for compliance with the principles set out in European regulations. | Open
|  | Consider creating your own template for data sharing and joint controllership agreements, especially towards (sub)processors. In this way, more uniformity is created in terms of data protection in the exchange of data. | Open
6 | Project Transparency |  | Open |  | Low |  | 1 | 2
|  | Make sure changes to the privacy statement are communicated to the data subjects. | Open
7 | Project Incident Management |  | Open |  | High |  | 1 | 1
|  | Include data breaches as a possible incident type in the incident management procedure. Add the data breach reporting flow in the process. | Open
|  | Make sure responsibilities regarding incidents and data breaches are clear. | Open
|  | Keep a register of all personal data breaches, reports, analyses and lessons learned. Share lessons learned with relevant employees. | Open
|  | Prepare escalation and communication of incidents to relevant authorities in detail. | Open
8 | Project Compliance |  | Open |  | Low
| 8.1 | Implement a process of continuous improvement that reflects that the stakeholders involved are aware of non-conformities and action points to improve them or considerations why they are maintained (internal audit, privacy and information security at management meetings). | Open
| 8.2 | Discuss with top management whether GDPR certification or ISO 27701 certification could potentially be a future goal. The implementation following this assessment could be tailored to these certification mechanisms. | Open
- External audit support (optioneel): depends on the external audit duration proposed by certification body.
- Security Officer (optional): flexible (1 day per week, 2 days per months, 1 day per month)

## Dataset
Open | Critical
Planned | High
Ongoing | Medium
Done | Low